## Risk Impact Matrix
SMDC Dashboard Initiative — Risk Impact Matrix
Score each risk on Likelihood (1–5) and each Impact dimension (1–5). Total Weighted Score = Likelihood × Average Impact.
Risk ID | Risk Name / Description | RBS Category | Likelihood (1–5) | Technical Impact (1–5) | Clinical Impact (1–5) | Regulatory Impact (1–5) | Financial Impact (1–5) | Reputational Impact (1–5) | Equity Impact (1–5) | Total Weighted Score | Priority Zone
R-01 | Alert threshold miscalibration causing false positives/negatives | Technical – Algorithms | 4 | 5 | 5 | 3 | 3 | 4 | 2
R-02 | EHR integration failures breaking real-time data feed | Technical – Integration | 3 | 5 | 4 | 3 | 4 | 3 | 1
R-03 | Dashboard UI inaccessible on low-bandwidth rural networks | Technical – Infrastructure | 3 | 3 | 4 | 1 | 2 | 3 | 5
R-04 | HIPAA breach due to unsecured PHI transmission | Regulatory – HIPAA | 2 | 2 | 4 | 5 | 5 | 5 | 2
R-05 | FDA classification as SaMD requires unexpected regulatory pathway | Regulatory – FDA | 3 | 1 | 3 | 5 | 5 | 4 | 1
R-06 | Clinician alert fatigue leading to ignored critical notifications | Clinical – Workflow | 4 | 2 | 5 | 2 | 3 | 4 | 3
R-07 | Patient misinterpretation of dashboard data causing self-treatment | Clinical – Patient Safety | 5 | 2 | 5 | 3 | 3 | 5 | 4
R-08 | Key engineer or clinician departure mid-project | Organizational – Staffing | 3 | 3 | 2 | 1 | 3 | 2 | 1
R-09 | Sponsor funding withdrawal due to scope creep | Financial – Funding | 2 | 2 | 2 | 1 | 5 | 4 | 2
R-10 | Cost overruns from repeated UX redesign cycles | Financial – Budget | 4 | 2 | 1 | 1 | 4 | 2 | 1
R-11 | Non-English-speaking patients excluded by English-only UI | Equity – Language | 4 | 1 | 3 | 2 | 2 | 4 | 5
R-12 | Low-income users lack devices to access dashboard | Equity – Access | 3 | 1 | 3 | 1 | 1 | 3 | 5
R-13 | Vendor API changes break third-party integrations post-launch | Technical – Integration | 3 | 4 | 3 | 2 | 3 | 3 | 1
R-14 | Informed consent process inadequate for data use | Regulatory – Consent | 2 | 1 | 3 | 4 | 2 | 4 | 3
R-15 | Dashboard data lag creates outdated clinical picture during emergencies | Clinical – Data Quality | 3 | 3 | 5 | 2 | 2 | 4 | 3

## Scoring Rubric
SMDC — Impact Scoring Rubric Reference
Score | Likelihood | Technical | Clinical | Regulatory | Financial | Equity / Reputational
1 | Very unlikely (<10% chance) | No functional impact; minor glitch | No clinical effect; patient unaware | No regulatory exposure; fully compliant | <$5K overrun; absorbed in budget | No loss of trust; no access barrier
2 | Unlikely (10–30%) | Degraded performance; user workaround exists | Mild confusion; no unsafe action taken | Minor documentation gap; correctable | $5K–$25K overrun; manageable | Minor reputational dent; small equity gap
3 | Possible (30–60%) | Feature unavailable; notable UX disruption | Moderate confusion; near-miss event possible | Audit flag; compliance delay likely | $25K–$100K overrun; requires reallocation | Visible public concern; subgroup excluded
4 | Likely (60–80%) | Core module fails; requires redesign sprint | Patient acts on bad data; adverse event risk | Regulatory sanction; FDA/HIPAA notice | $100K–$500K overrun; funding at risk | Major trust damage; significant equity harm
5 | Very likely (>80%) | System-wide failure; project halted | Documented patient harm; incident report | Enforcement action; project shut down | >$500K overrun; project collapse | Systemic exclusion; project discredited