Appendix: Impact Weighting Guide

Milestone 2 — Advanced Scoring Reference

SMDC Dashboard Initiative  |  Risk Management Practicum

# Overview

The standard Risk Impact Matrix treats all six impact dimensions equally. For health equity-focused projects like SMDC, teams may apply differential weighting so that high-stakes dimensions are not masked by lower-urgency scores. This guide explains when and how to apply weights.

# Impact Dimension Reference

| Dimension | Default Weight | What It Captures | When to Increase Weight |
| --- | --- | --- | --- |
| Technical | Equal (1.0x) | System reliability, data accuracy, uptime, algorithm performance | When technical failure directly disables core functionality |
| Clinical | Elevated (1.5x suggested) | Patient safety, clinician workflow, care quality impact | Always — patient safety is the primary mission driver |
| Regulatory | Elevated (1.5x suggested) | HIPAA, FDA, IRB, consent, legal liability | When operating in a novel regulatory space (e.g., SaMD ambiguity) |
| Financial | Equal (1.0x) | Budget impact, funding risk, cost of remediation | When operating near grant milestone deadlines |
| Reputational | Equal (1.0x) | Trust from patients, clinicians, investors, community | When project is publicly visible or in high-scrutiny sector |
| Equity | Elevated (1.25x suggested) | Access barriers, exclusion of marginalized groups, language gaps | When project mission explicitly includes health equity goals |

# Scoring Formulas

| Scoring Method | Formula | When to Apply |
| --- | --- | --- |
| Simple average (default) | Likelihood x AVERAGE(T, C, R, F, Rep, Eq) | Use when no dimension is prioritized over others |
| Weighted average (advanced) | Likelihood x [(T*1 + C*1.5 + R*1.5 + F*1 + Rep*1 + Eq*1.25) / 7.25] | Use for health equity-focused projects like SMDC |
| Clinical override flag | If Clinical Impact >= 4, flag HIGH regardless of total score | Ensures patient safety risks never fall through the cracks |

## Example: Weighted vs. Unweighted Score

Risk R-07 (Patient self-treatment based on misread data): Likelihood = 5, Scores: T=2, C=5, R=3, F=3, Rep=5, Eq=4

- Unweighted: 5 x AVERAGE(2,5,3,3,5,4) = 5 x 3.67 = 18.3 → HIGH

- Weighted:   5 x [(2 + 7.5 + 4.5 + 3 + 5 + 5) / 7.25] = 5 x 3.72 = 18.6 → HIGH (elevated emphasis on patient safety)

- Clinical Override: Clinical Impact = 5 >= 4 → Automatically flagged HIGH regardless of total score

# When to Use Each Approach

- Use simple average when working quickly or when your team lacks consensus on weights.

- Use weighted average when presenting to stakeholders for whom specific dimensions carry policy significance.

- Always apply the Clinical Override flag in any health technology project.

- Document your chosen approach in your Risk Themes Memo so reviewers understand your methodology.

## Team Calibration Exercise (Recommended — 15 minutes)

- Choose 2 risks from your RBS as calibration cases.

- Have each person score independently, then compare.

- Discuss outliers (scores differing by 2+ points).

- Agree on shared definitions for scores 3, 4, and 5 in each dimension.

- Document the agreed definitions in this appendix before starting full scoring.