Control Design Mini Guide

Milestone 4 — Appendix Reference for Preventive Control Design

SMDC Dashboard Initiative  |  Risk Management Practicum  |  Milestone 4

# What Is a Preventive Control?

A preventive control is a proactive structure — a named action, protocol, or process — that reduces the probability or magnitude of a specific risk event before it occurs. It is not a plan to respond after things go wrong; it is a mechanism that makes going wrong harder.

In the SMDC context: if 'alert threshold miscalibration' is the risk, a preventive control is 'validate thresholds against 30 days of patient data before every sprint release.' Not 'review alerts if clinicians complain.'

# Preventive Controls vs. Reactive Responses

| Dimension | PREVENTIVE Control | REACTIVE Response |
| --- | --- | --- |
| Purpose | Reduce probability the risk occurs | Address damage after the risk materializes |
| Timing | Before the risk event | After the risk event |
| Example | Validate alert thresholds before sprint ships | Review alert logic after clinician complaints |
| Milestone 4 focus? | YES — this is what you are designing | NO — this is future-milestone territory |
| Strength | Stops harm before it happens; builds team confidence | Necessary but insufficient; does not restore lost trust or data |
| Weakness | Requires discipline and ownership before problems are visible | Always reactive to damage already done; expensive |

Milestone 4 asks for preventive controls only. Reactive responses are important — but they belong in future milestones focused on monitoring, incident management, and contingency planning.

# The Seven Elements of a Well-Designed Control

Every control in your checklist must include all seven elements. Missing any one makes the control unimplementable.

| Element | Definition and Example |
| --- | --- |
| Control Name | A short, precise, action-oriented label. WEAK: 'Monitor alerts.' STRONG: 'Alert Threshold Calibration Review — Pre-Sprint Validation.' |
| Control Owner | One named role (not a team or 'everyone'). The owner is accountable for execution AND for signaling when the control is at risk. Example: 'Clinical Informatics Lead.' |
| Timing & Frequency | A specific schedule: 'Before each sprint release' or 'Monthly during pilot, weekly during launch week.' Not: 'regularly' or 'as needed.' |
| Mechanism | The exact task or process. Who does what using which tool or data source? Example: 'Clinical Informatics runs threshold validation protocol against 30-day patient historical data. False-positive rate must be <5% per condition.' |
| Evidence of Completion | What proves it was done? Signed report, survey results log, test certificate, email approval on file. If you can't prove it happened, it didn't count. |
| Warning Sign (Trigger) | What signals the control is failing — BEFORE failure is catastrophic? Example: 'False-positive rate exceeds 5% in sprint review' OR 'Clinician survey shows >20% report ignoring alerts.' |
| Dependencies | What does this control rely on to function? Examples: EHR vendor data access, specific role availability, third-party tool, budget line item. Name them — hidden dependencies are where controls collapse. |

# Selecting Your Risk Theme

Your control checklist should target one risk theme from your Milestone 3 synthesis. Choose a theme that is:

| Strong Theme Choice | Weak Theme Choice | Why It Matters |
| --- | --- | --- |
| Clinical Interpretation Risk — Alert Design and Health Literacy Gap | 'Clinical risks' or 'patient issues' | Specific themes yield specific controls. Vague themes yield vague checklists that can't be implemented. |
| Scope to 3–5 specific risk drivers | Trying to cover all 15 RBS risks | Controls only work when tightly scoped. Narrow the theme; go deep rather than broad. |
| Actionable by project team in the current MVP cycle | Risks that depend on post-launch data | Controls must be implementable now. Future-dependent controls belong in Milestone 9 (Monitoring). |
| Supported by Milestone 3 stakeholder consensus or urgency | Risks with no stakeholder validation | Controls built without stakeholder input may address the wrong mechanism or duplicate existing processes. |

Example themes from the SMDC risk matrix: Alert Interpretation Risk (R-01, R-06, R-07), EHR Integration Fragility (R-02, R-13), Equity and Language Access Barriers (R-08, R-12), Regulatory Compliance Gaps (R-04, R-05).

# Decomposing a Theme Into Risk Drivers

Once you've selected your theme, break it into 3–5 specific risk drivers — the individual failure modes within the larger pattern.

EXAMPLE THEME: Clinical Interpretation Risk
Risk Driver 1: Alert thresholds miscalibrated — false positives desensitize clinicians
Risk Driver 2: Alert fatigue causes all alerts to be ignored
Risk Driver 3: Data lag makes dashboard picture outdated during emergencies
Risk Driver 4: Patients misread dashboard data and make unsafe decisions
Risk Driver 5: No shared protocol for responding to specific alert severity levels

Each driver gets one control. Controls are not catch-all responses to the whole theme — they are targeted interventions against specific mechanisms.

# The Control Design Process — Step by Step

- Start with the risk driver. Write it as a specific failure statement: '[X condition] causes [Y consequence].'

- Identify the MECHANISM of failure. How exactly does this risk materialize? What is the triggering condition?

- Design the control to interrupt the mechanism — not just to respond to the consequence.

- Assign ownership to the role with the most leverage to interrupt that specific mechanism.

- Define timing: at what point in the project lifecycle does this control have maximum effect?

- Build the evidence requirement: what would you show an auditor to prove this control ran?

- Name the warning sign: what observable, measurable signal tells you the control is eroding?

# Control Quality Self-Check

Before submitting, verify each control passes this test:

- Could a new team member execute this control from the description alone, without asking for clarification?

- Is there exactly one named owner — not 'the team'?

- Does the timing specify a concrete schedule, not 'regularly'?

- Does the evidence field describe a retrievable artifact — not 'team agrees it was done'?

- Does the warning sign describe something observable before catastrophic failure — not after?

- Does the control protect all users, including non-English-speaking and low-income patients?

# Common Control Design Mistakes

- Writing aspirations instead of controls: 'Ensure patient safety' is a value. 'Validate all patient-facing content against Flesch-Kincaid grade 6 or below before shipping' is a control.

- Assigning control ownership to 'the team': When everyone owns it, no one owns it. Name one role.

- Designing controls that cannot be evidenced: If completion can't be documented, the control is unverifiable and therefore unenforceable.

- Ignoring equity in control design: A usability test with English-only participants does not control for language access risk. Build inclusion into the mechanism.

- Confusing monitoring with prevention: Monitoring tells you when something has gone wrong. Prevention reduces the chance it goes wrong at all. Both are needed; they are not the same thing.

- Forgetting dependencies: A control that depends on a vendor API, a specific clinician's availability, or an unconfirmed tool license is fragile. Name the dependency and have a backup.